## for all last endpoints you make
Old Project |  | New Project
Category | Endpoint | BackEnd | FrontEnd | Embedded | Notes
Auth | Login(/api/Auth/LoginUser) | Done | Done | No Need
Auth | GetAllUsers(/api/Auth/GetAllUsers) | Done | Done | No Need
Auth | CreateUser(/api/Auth/CreateUser) | Done | Done | No Need
Auth | GetUserById(/api/Auth/GetUserById/{id}) | Done | Done | No Need
Auth | UpdateUser(/api/Auth/UpdateUser/{id}) | Done | Done | No Need
Auth | DeleteUser(/api/Auth/DeleteUser/{id}) | Waiting | Waiting | No Need
Auth | ChangePassword(/api/Auth/ChangePassword) | Done | Waiting | No Need
Auth | SetNewPasswordToSpecificUser(/api/Auth/SetNewPasswordToSpecificUser) | Done | Waiting | No Need
Auth | LockOrUnlockUser(/api/Auth/LockOrUnlockUser) | Done | Waiting | No Need
Auth | ListOfUsers(/api/Auth/ListOfUsers) | Waiting | Waiting | No Need
Lookups | GetAllCountries(/api/Lookups/GetAllCountries) | Done | Done | No Need
Lookups | GetAllStates/{id}(/api/Lookups/GetAllStates/{id}) | Done | Done | No Need
Lookups | GetAllCategories(/api/Lookups/GetAllCategories) | Done | Done | No Need
Lookups | CreateCategory(/api/Lookups/CreateCategory) | Done | Done | No Need
Lookups | UpdateCategory/{id}(/api/Lookups/UpdateCategory/{id}) | Done | Done | No Need
Lookups | DeleteCategory/{id}(/api/Lookups/DeleteCategory/{id}) | Done | Done | No Need
Notifications | GetNotificationsCountToSpecificUser(/api/Notifications/GetNotificationsCountToSpecificUser) | Waiting | Waiting | No Need
Notifications | GetAllNotificationsToSpecificUser(/api/Notifications/GetAllNotificationsToSpecificUser) | Waiting | Waiting | No Need
Notifications | CreateNotificationToSpecificUser(/api/Notifications/CreateNotificationToSpecificUser) | Waiting | Waiting | No Need
Reading | Reading(/api/Reading) | Done | No Need | Done | تم استبدالهم | CreateTrapReading (api/TrapRead/CreateTrapReading)
Reading | Reading2(/api/Reading2) | Done | No Need | Done
Reports | GetTrapReport/{id}(/api/Reports/GetTrapReport/{id}) | Waiting | Waiting | No Need
Trap Emergencies | GetAllTrapEmergencies/{serialNumber}(/api/TrapEmergencies/GetAllTrapEmergencies/{serialNumber}) | Done | InProgress | No Need
Trap Emergencies | GetAllTrapEmergenciesNew/{serialNumber}(/api/TrapEmergencies/GetAllTrapEmergenciesNew/{serialNumber}) | Done | InProgress | No Need
Trap Emergencies | CreateTrapEmergency(/api/TrapEmergencies/CreateTrapEmergency) | Done | InProgress | No Need
Trap Emergencies | AddTrapEmergency(/api/TrapEmergencies/AddTrapEmergency) | Done | InProgress | No Need
Trap Readings | GetAllSpecTrapReadings(/api/TrapReadings/GetAllSpecTrapReadings) | Waiting | Waiting | No Need
Trap Readings | GetAllTrapReadings(/api/TrapReadings/GetAllTrapReadings) | Done | Done | No Need | سيتم مراعة التفاصيل عند البدء
Trap Readings | GetAllTrapReadingsNew(/api/TrapReadings/GetAllTrapReadingsNew) | No Need | No Need | No Need
Trap Readings | GetAllTrapReadingsPerDay(/api/TrapReadings/GetAllTrapReadingsPerDay) | Waiting | Waiting | No Need
Trap Readings | CreateTrapReading(/api/TrapReadings/CreateTrapReading) | Done | No Need | Done
Trap Readings | GetLastReadingForAllTraps(/api/TrapReadings/GetLastReadingForAllTraps) | Waiting | Waiting | No Need
Trap Readings | GetLastReadingToSpecifiedTrap/{trapId}(/api/TrapReadings/GetLastReadingToSpecifiedTrap/{trapId}) | Waiting | Waiting | No Need
Trap Readings | GetLastReadingToSpecifiedAllEmptyValueILatAndLongTrap/{trapId}(/api/TrapReadings/GetLastReadingToSpecifiedAllEmptyValueILatAndLongTrap/{trapId}) | Waiting | Waiting | No Need
Trap Readings | GetLastReadingToCurrentUserTraps(/api/TrapReadings/GetLastReadingToCurrentUserTraps) | Waiting | Waiting | No Need | سيتم مراعة التفاصيل عند البدء
Trap Readings | GetLastReadingToCurrentUserTrapsNew(/api/TrapReadings/GetLastReadingToCurrentUserTrapsNew) | Waiting | Waiting | No Need
Trap Readings | GetLastReadingToCurrentUserTrapsNew1(/api/TrapReadings/GetLastReadingToCurrentUserTrapsNew1) | Waiting | Waiting | No Need
Trap Readings | GetStatisticsOfTrapsOnlyCurrentUser(/api/TrapReadings/GetStatisticsOfTrapsOnlyCurrentUser) | Waiting | Waiting | No Need
Trap Readings | StopNotificationToSpecifiedUserAsync(/api/TrapReadings/StopNotificationToSpecifiedUserAsync) | Waiting | Waiting | No Need
Trap Readings | GetAllCurrentUserNotifications(/api/TrapReadings/GetAllCurrentUserNotifications) | Waiting | Waiting | No Need
Trap Readings | GetStatisticsForAllTrapsReadingsAsInsects(/api/TrapReadings/GetStatisticsForAllTrapsReadingsAsInsects) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesToLastSixMonthsForTrap/{trapId}(/api/TrapReadings/GetCountOfMosuqitoesToLastSixMonthsForTrap/{trapId}) | Waiting | Waiting | No Need
Trap Readings | GetStatisticsForTrapReadingsAsInsects/{trapId}(/api/TrapReadings/GetStatisticsForTrapReadingsAsInsects/{trapId}) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesPerMonth(/api/TrapReadings/GetCountOfMosuqitoesPerMonth) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesInDayOfMonthOfYear(/api/TrapReadings/GetCountOfMosuqitoesInDayOfMonthOfYear) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesPerSevenDays(/api/TrapReadings/GetCountOfMosuqitoesPerSevenDays) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesPerSevenDaysForSpecificTrap/{trapId}(/api/TrapReadings/GetCountOfMosuqitoesPerSevenDaysForSpecificTrap/{trapId}) | Waiting | Waiting | No Need
Trap Readings | GetTotalAllTrapReadingsToToday(/api/TrapReadings/GetTotalAllTrapReadingsToToday) | Waiting | Waiting | No Need
Trap Readings | GetAllTrapsStatus(/api/TrapReadings/GetAllTrapsStatus) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesToLast12Months(/api/TrapReadings/GetCountOfMosuqitoesToLast12Months) | Waiting | Waiting | No Need
Trap Readings | GetCountOfMosuqitoesTo12MonthsForSpecificTrap/{trapId}(/api/TrapReadings/GetCountOfMosuqitoesTo12MonthsForSpecificTrap/{trapId}) | Waiting | Waiting | No Need
Traps | ListOfTraps(/api/Traps/ListOfTraps) | Done | Done | No Need
Traps | GetAllTraps(/api/Traps/GetAllTraps) | Done | Done | No Need
Traps | GetAllTrapsWithoutPagination(/api/Traps/GetAllTrapsWithoutPagination) | InProgress | InProgress | No Need | Canceled
Traps | CreatTrap(/api/Traps/CreatTrap) | Done | Done | No Need
Traps | GetTrapById/{id}(/api/Traps/GetTrapById/{id}) | InProgress | InProgress | No Need
Traps | TrapFilterByCategory/{id}(/api/Traps/TrapFilterByCategory/{id}) | InProgress | InProgress | No Need | Canceled
Traps | TrapLogsReport/{id}(/api/Traps/TrapLogsReport/{id}) | Waiting | Waiting | No Need
Traps | UpdateTrap/{id}(/api/Traps/UpdateTrap/{id}) | InProgress | InProgress | No Need
Traps | DeleteTrap/{id}(/api/Traps/DeleteTrap/{id}) | InProgress | InProgress | No Need
Traps | LoadData2(/api/Traps/LoadData2) | Done | No Need | Done | api/LoadConfigurations
Traps | LoadData2Logs(/api/Traps/LoadData2Logs) | InProgress | InProgress | InProgress